# Microsoft 365 Implementation and Governance Strategy

Accepted Project Proposal – Nordica Insurance S.A.

BearingPoint

January – July 2024

Table of Contents

# Microsoft 365 Implementation and Governance Strategy

Client: Nordica Insurance S.A. Industry: Financial Services – Insurance Engagement Period: January 2024 – July 2024 (7 months) Engagement Type: Microsoft 365 Deployment & Governance Status: Accepted and Successfully Completed

## 1. Client Background

Nordica Insurance S.A. is an insurance company headquartered in Bucharest with 1,800 employees distributed across a national branch network. The company relied on an on-premise email infrastructure (Exchange 2013) and a mix of disparate collaboration tools (Skype for Business, shared network drives, unauthorized Dropbox usage). The need to modernize the collaboration platform, the growth in remote work post-pandemic, and compliance requirements from the insurance regulatory body were the primary drivers for adopting Microsoft 365.

## 2. Project Team

| Name | Role | Area of Expertise |
| --- | --- | --- |
| Cristina Dumitru | M365 Lead Consultant | Microsoft 365, Exchange Online, SharePoint |
| Katharina Müller | Change Management Lead | Technology adoption, organizational training |
| Andrei Stancu | Security & Compliance Specialist | Zero Trust, DLP, Purview, Entra ID |
| Ioana Vlad | Business Analyst | Functional requirements, business processes |
| Ana-Maria Popescu | Project Manager | Governance, stakeholder management |

## 3. Project Scope and Objectives

- Fully migrate 1,800 mailboxes from Exchange 2013 on-premise to Exchange Online

- Implement Microsoft Teams as the unified collaboration and communication platform

- Configure SharePoint Online for departmental document management

- Develop and implement an M365 governance framework (naming conventions, Teams creation policies, lifecycle management)

- Configure security and compliance policies aligned with FSA (Financial Supervisory Authority) requirements

- Execute a comprehensive adoption program (change management) for all users

## 4. Technologies Used

- Microsoft Exchange Online: Cloud email service

- Microsoft Teams: Unified communication, video conferencing, chat

- SharePoint Online: Document management, departmental sites

- Microsoft Entra ID (Azure AD): Identity management, SSO, MFA

- Microsoft Intune: Mobile device management (MDM/MAM)

- Microsoft Purview: Data classification, DLP, audit and compliance

- Microsoft Viva Engage (Yammer): Organization-wide internal communication

- ADMT + Exchange Hybrid: Hybrid Exchange migration tooling

## 5. Implementation Steps

### Phase 1 – Design & Governance (January – February 2024)

Workshops were held with all departments to gather requirements. A Governance Framework document was developed covering: Teams structure (channel types, naming conventions), data retention policies (1 year/5 years/permanent by document category), and information classification levels (Public, Internal, Confidential, Strictly Confidential). Initial M365 tenant configuration and security baseline settings were applied.

### Phase 2 – Pilot (February – March 2024)

Pilot conducted with the IT department (120 users): full configuration, Exchange Hybrid testing, and first training session. Mailbox migration procedures and security settings were validated.

### Phase 3 – Email Migration and Teams Rollout (March – May 2024)

Migration was executed in 6 batches of approximately 300 users each, with every batch preceded by a 2-hour training session. Teams was activated simultaneously with mailbox migration. Skype for Business was progressively decommissioned.

### Phase 4 – SharePoint and Compliance (May – June 2024)

Departmental SharePoint sites were created and approximately 4 TB of documents were migrated from network drives. Purview DLP policies and sensitivity labels were implemented. Intune was configured for mobile devices.

### Phase 5 – Stabilization and Adoption (July 2024)

Advanced adoption sessions for Power Users, M365 Usage Analytics configuration, post-launch incident remediation, and operational documentation for the internal IT team.

## 6. Challenges Encountered and Solutions

Challenge 1 – Oversized mailboxes 47 mailboxes exceeded 50 GB (the Exchange Online limit without an Enterprise license). Solution: Cristina Dumitru created a PowerShell archiving script and configured Online Archive for these accounts, reducing sizes before migration.

Challenge 2 – DLP policies blocking legitimate business flows Conservatively configured DLP policies were blocking internal document sharing containing insurance data between departments. Solution: Andrei Stancu created exceptions based on security groups and refined DLP rules after analyzing 3 weeks of audit logs.

Challenge 3 – Sales agent resistance to Teams Sales agents accustomed to phone calls refused to adopt Teams. Solution: Katharina Müller organized role-specific demonstration sessions focused on concrete agent benefits (document sharing with clients, screen-sharing video calls) and launched a Teams Champions program.

Challenge 4 – Disorganized content during SharePoint migration Network drives contained duplicate files and inconsistent folder structures accumulated over 15 years. Solution: SharePoint Migration Tool was used with pre-processing via Python scripts for deduplication and folder structure normalization before migration.

## 7. Collaboration Model

BearingPoint operated predominantly remote with weekly on-site visits to the Bucharest headquarters. A dedicated project Team (created in M365 itself) with phase-specific channels, a project SharePoint site with all deliverables, and an active post-launch support channel were maintained for 60 days.

## 8. Results Achieved

- 100% of users migrated within the planned timeline

- Teams adoption rate at 30 days: 87% weekly active users

- Complete elimination of Skype for Business and unauthorized Dropbox usage

- Zero data-related security incidents in the first 6 months

- Estimated savings of €340,000/year compared to on-premise infrastructure

## 9. Lessons Learned

- The Governance Framework must be defined before any deployment: Without clear rules from the start, users create chaotic structures that are very costly to remediate later.

- Role-specific training delivers far greater ROI than generic sessions: Sales agents adopted faster after dedicated sessions compared to all other user groups.

- Data classification is a project in its own right: Underestimating the time required for SharePoint document inventory and classification extended Phase 4 by 3 weeks.